IdentiFind

Mobile Application — Development Plan

| Version 1.0 | Date May 2026 | Target Release Q4 2026 | Platforms iOS & Android |
| --- | --- | --- | --- |

1. OVERVIEW

This document outlines the plan to develop native iOS and Android mobile applications for IdentiFind, the identity monitoring and PII discovery platform. The mobile apps will surface all existing web features — risk scores, security findings, breach alerts, account management, and PII exposure reports — optimized for mobile, with the addition of real-time push notifications for critical security events.

The existing backend (Next.js API routes, Prisma/Supabase database, scan pipeline) requires minimal changes. The mobile application is a new client consuming the existing API, meaning the scan engine, breach detectors, PII brokers, and security scoring logic ship to mobile automatically.

2. TECHNOLOGY STACK

Framework: React Native with Expo

React Native with Expo is the recommended framework for the following reasons:

Existing codebase is React/TypeScript — component patterns, hooks, and types transfer directly

TypeScript types (PiiRecord, BreachRecord, ScoredFinding, etc.) are shared between web and mobile with no duplication

Expo handles build pipelines, app store submission (EAS Build), and push notification delivery (Expo Notifications)

Expo Router uses the same file-system routing paradigm as Next.js App Router — consistent mental model

Single codebase targets both iOS and Android; no Swift/Kotlin split

Alternatives Considered

| Option | Pro | Con |
| --- | --- | --- |
| Flutter / Dart | High performance, good UI | No code sharing with existing TS codebase; team must learn Dart |
| Native Swift + Kotlin | Best performance, full platform APIs | Two separate codebases; 2x maintenance; longest timeline |
| PWA (web wrapper) | Zero new codebase, instant deploy | iOS push notifications unreliable; no biometric auth; app store rejection risk |
| Capacitor / Ionic | Wraps existing Next.js app quickly | Web performance in native shell; complex OAuth redirects |

3. ARCHITECTURE

What Stays the Same

The entire backend is reused without modification:

Next.js API routes: /api/scan, /api/alerts, /api/accounts, /api/settings/*

Scan orchestrator and all scanner modules (breach, PII broker, username, crt.sh)

Prisma schema and Supabase PostgreSQL database

NextAuth session management — mobile uses the same auth endpoints via browser handoff

Encryption, audit logging, and security engine

New Backend Additions (Minimal)

Push token endpoint — POST /api/notifications/register stores an Expo push token per user session

Notification dispatch — added to scan orchestrator: fires a push when CRITICAL or HIGH findings are returned

Scheduled scan trigger — Vercel Cron Job that auto-triggers daily scans per user for background alerts

Mobile Client Architecture

Expo Router for file-system navigation (tabs: Dashboard, Alerts, Accounts, Profile)

React Query for data fetching, caching, and background refetch from the Next.js API

expo-secure-store for encrypted session token storage (replaces browser cookies)

expo-notifications for push notification registration and foreground/background handling

expo-local-authentication for biometric lock screen (Face ID / fingerprint)

expo-auth-session for OAuth provider flows (Google, GitHub, LinkedIn, Twitter, Facebook)

4. FEATURE PARITY

All existing web features are included. Mobile adds three new capabilities:

| Feature | Web | Mobile |
| --- | --- | --- |
| Risk score dashboard | ✓ | ✓ |
| Security findings list | ✓ | ✓ |
| Connected accounts management | ✓ | ✓ |
| Breach alerts | ✓ | ✓ |
| Impersonation alerts | ✓ | ✓ |
| PII exposure report | ✓ | ✓ |
| Manual scan trigger | ✓ | ✓ |
| Profile & settings | ✓ | ✓ |
| Push notifications | — | ✓ (NEW) |
| Biometric lock (Face ID / FP) | — | ✓ (NEW) |
| Background / scheduled scans | — | ✓ (NEW) |

5. DEVELOPMENT PHASES

| Phase 1 | Foundation June 2026 |
| --- | --- |

Initialize Expo project with TypeScript, Expo Router, and EAS Build configuration

Implement OAuth login flow via expo-auth-session connecting to existing NextAuth backend

Build tab navigation shell: Dashboard, Alerts, Accounts, Profile

Wire up React Query to the existing Next.js API

Implement expo-secure-store for session token persistence

Verify full auth round-trip on iOS Simulator and Android Emulator

Goal: authenticated user can log in and see their live data on both platforms

| Phase 2 | Core Screens July – Aug 2026 |
| --- | --- |

Dashboard: risk score ring, finding counts, last-scanned timestamp, pull-to-refresh scan trigger

Alerts screen: breach, impersonation, and PII findings with severity badges

Alert detail: full description, recommended action, resolve button

Accounts screen: connected social accounts list, add/remove account flow

Profile screen: name, email, phone verification status

Settings: notification preferences, scan frequency, biometric toggle, sign out

Loading skeletons and empty states for all screens

| Phase 3 | Push Notifications September 2026 |
| --- | --- |

Add POST /api/notifications/register to store Expo push tokens

Register for push permissions on app launch; send token to backend

Add notification dispatch to scan orchestrator for CRITICAL/HIGH findings

Set up Vercel Cron Job for daily automated scans per active user

Handle foreground notification display and navigation to relevant alert

Handle background notification tap with deep-link to specific finding

Test full push delivery loop on physical devices (required for push testing)

| Phase 4 | Polish & Security October 2026 |
| --- | --- |

Biometric authentication gate on app open via expo-local-authentication

Auto-lock after configurable inactivity period

Haptic feedback on critical alerts

Dark mode support matching the existing brand palette

Accessibility audit (VoiceOver / TalkBack) on all screens

Error boundary and crash reporting (Sentry via @sentry/react-native)

Offline state handling — graceful degradation when network is unavailable

| Phase 5 | Beta & Submission November 2026 |
| --- | --- |

Internal TestFlight build for iOS; Internal Testing track for Android

Structured QA pass across iPhone and Android physical devices

App Store Connect: screenshots, description, privacy policy, data usage labels

Google Play Console: store graphics, content rating, data safety section

Submit for review (Apple: 1–7 days typical; Google: 1–3 days typical)

Address any rejection feedback and resubmit

| Phase 6 | Launch Buffer December 2026 |
| --- | --- |

Monitor crash reports and ANRs from production users

Patch high-priority issues in rapid follow-up builds

Collect early user feedback on notification frequency and UX

Plan v1.1 backlog: Reddit/Discord/TikTok clients, iOS home screen widget, watchOS complication

6. TIMELINE SUMMARY

| Phase | Focus | Month | Milestone |
| --- | --- | --- | --- |
| 1 | Foundation | June | Auth works on both simulators |
| 2 | Core Screens | July – Aug | All web features visible on mobile |
| 3 | Push Notifications | September | Alerts firing on physical devices |
| 4 | Polish | October | Biometrics, dark mode, accessibility |
| 5 | Beta & Submission | November | Live on TestFlight + Play Internal Testing |
| 6 | Launch Buffer | December | v1.0 public — monitor & patch |

7. RISKS & MITIGATIONS

OAuth flow on mobile

Mobile OAuth requires browser redirects and deep-link callbacks — more complex than web. Mitigation: expo-auth-session handles this pattern; implement and validate in Phase 1 before any other work.

Apple App Store review

Apps handling personal identity data may require additional privacy review. Mitigation: prepare a clear privacy policy, accurate data-usage labels, and a demo account for reviewers. Allow 2–3 week buffer in Phase 5.

Push notification opt-in rates

iOS requires explicit user permission; some users will decline. Mitigation: request permission contextually after a scan finds something, not on first launch.

Expo managed vs. bare workflow

Some native modules may require ejecting from the Expo managed workflow. Mitigation: audit all required native modules before scaffolding; start with bare workflow if any module requires it.

iOS background execution limits

iOS heavily throttles background app refresh — full scans cannot reliably run on the client. Mitigation: run scans server-side via cron and push results to the device. No background execution required on the client.

8. PHASE 1 SCAFFOLD — TECHNICAL DETAIL

Completion is defined as: an authenticated user can log in via OAuth on both an iOS Simulator and Android Emulator, navigate the tab shell, and see their live risk score and findings pulled from the existing API.

1. Initialize Expo project

npx create-expo-app@latest identifind-mobile --template tabs
Configure TypeScript strict mode, Expo Router, and path aliases matching the web project.

2. Install core dependencies

expo-auth-session, expo-secure-store, expo-local-authentication, expo-notifications, @tanstack/react-query.

3. Configure EAS Build

eas build:configure — sets up iOS and Android build profiles for simulator development builds.

4. Implement authentication

expo-auth-session initiates OAuth flows; NextAuth /api/auth/* endpoints handle tokens unchanged. Session token is persisted to expo-secure-store.

5. Build navigation shell

Four tabs: Dashboard, Alerts, Accounts, Profile. Each screen fetches from the existing Next.js API using the stored session token.

6. Dashboard data fetch

GET /api/scan retrieves the last scan result. Render risk score and finding counts. Pull-to-refresh triggers POST /api/scan and refetches.

7. Validate on both platforms

Run on iOS Simulator and Android Emulator. Confirm auth, navigation, and data fetch work end-to-end.

— End of Document —